## 00_Overview
Grapevine Pedigree Atlas — Data Curation Tracker
Version: April 1, 2026 ¦ Brandon Roy
Purpose | This workbook tracks every literature source and supplementary dataset needed to maximise pedigree coverage in the Grapevine Pedigree Atlas. Each sheet represents one category of work. Work through Sheets 01→05 in order.
Sheet 01 | PRIORITY QUEUE — all new sources to obtain, ordered by integration impact. Start here.
Sheet 02 | ALREADY INTEGRATED — existing data layers for reference.
Sheet 03 | DATA QUALITY FIXES — internal issues found during validation that require your attention (no downloads needed).
Sheet 04 | SUPPLEMENTARY FILE GUIDE — exactly which file(s) to download from each paper (main text, supplement numbers, data repositories).
Sheet 05 | INTEGRATION ROADMAP — ordered pipeline showing which script to write/run after each download.
Status Legend
⬜ TODO | Not yet obtained — Brandon needs to download
📥 DOWNLOADED | File in hand — ready for integration
⚙️ PROCESSING | Script being written / data being parsed
✅ DONE | Fully integrated into the Atlas pipeline
⚠️ BLOCKED | Access/licensing barrier — note workaround

## 01_Priority_Queue
Data Curation Priority Queue — Sources to Obtain
# | Source / Paper | Authors | Year | Journal | DOI | Data Type | What to Download | Why Needed / Integration Value | Priority | Status
1 | Italian Parentage Atlas (Lacombe & Emanuelli et al.) | Lacombe T., Emanuelli F., et al. | 2020/2021 | Frontiers in Plant Science | 10.3389/fpls.2020.605934 | SNP-based parentage (Vitis18K chip) | Main paper PDF + Supplementary Tables 2 & 3 (PO pairs + PPO trios) From: frontiersin.org | INTEGRATED Apr 2026: SupplementaryFile5 (829 PO duos) + SupplementaryFile7 (189 trios) → 1,716 rows, 775 unique child varieties. Confirmed 34 rows, probable 1,676, disputed 6. Integrated into lacombe_emanuelli_2020_marker_support.csv. Also: Laucou 2018 (10K SNPs, pone.0192540) integrated separately → 1,196 rows, 460 unique children. | 🔴 CRITICAL | ✅ DONE
2 | Lacombe et al. 2013 — MOESM7 (Unrelated SSR) [Already have MOESM2] | Lacombe T. et al. | 2013 | Theor. Appl. Genet. | 10.1007/s00122-012-1988-2 | SSR profiles (20 nSSR loci) 276 unrelated reference varieties | Supplementary file MOESM7 only (276 reference varieties with full allele profiles) From: link.springer.com | DOWNLOADED Apr 2026: 122_2012_1988_MOESM7_ESM.pdf is the variety LIST (passport data for 276 reference varieties with VIVC IDs and geographic groups) — NOT the allele profile matrix. Allele matrix may be in MOESM3-6 or was never published as a table. Variety list saved as moesm7_vassal_varieties.csv (269 varieties extracted). The SSR allele profiles themselves still need to be obtained (check MOESM3 or contact INRA Vassal). | 🔴 CRITICAL | 📥 DOWNLOADED
3 | Sefc et al. 2000 — Allele Frequency Reference Panel | Sefc K.M. et al. | 2000 | Theor. Appl. Genet. | 10.1023/A:1018609920920 | SSR allele frequencies (OIV 9-locus GENRES081 panel) | Main paper PDF (Tables 2–3: allele frequencies per locus across 164 varieties) From: link.springer.com | DOWNLOADED Apr 2026: PDF in hand. Paper covers VVS2, VVMD5, VVMD7, VrZAG21, VrZAG47, VrZAG62, VrZAG64, VrZAG79, VrZAG83 — ONLY 5 of the 9 OIV loci (missing VVMD25, VVMD27, VVMD28, VVMD32). Tables contain regional diversity stats (He, Ho, FST) NOT per-allele frequencies. Per-allele frequency tables are NOT published in this paper. Need an alternative source for OIV panel allele frequencies (e.g. Lacombe 2013 Supp, or Laucou 2011 to compute empirical frequencies). | 🔴 CRITICAL | 📥 DOWNLOADED
4 | Laucou et al. 2011 — Large-scale kinship analysis [⚠️ DOI INVALID — see notes] | Laucou V. et al. | 2011 | PLOS ONE | 10.1371/journal.pone.0021265 | SSR profiles ~2,500 accessions 20 nSSR loci | INVALID — DO NOT PURSUE | DOI INVALID Apr 2026: 10.1371/journal.pone.0021265 resolves to a marine LiDAR/benthic communities paper — unrelated to grapevine. The 'Laucou 2011, 2500-accession SSR study' does not exist as a standalone publication. This entry was a cataloguing error. The large-scale SSR work for this group is Lacombe et al. 2013 (already integrated). The 783-cultivar SSR data from Laucou 2018 is also integrated. Remove from active queue — no action needed. | 🔴 CRITICAL | ⚠️ BLOCKED
5 | Magris et al. 2021 — 204 WGS Genomes | Magris G., Jurman I., Fornasiero A. et al. | 2021 | Nature Communications | 10.1038/s41467-021-27487-y | WGS resequencing 204 V. vinifera accessions 8–90x coverage | Supplementary Data 1 (sample metadata + accession IDs) + Supplementary Data 2 or 3 (kinship/IBD matrix if provided) From: nature.com/articles/... | WGS-level IBD coefficients for 204 accessions including key wine varieties (Cab Sauv, Pinot Noir, Chardonnay, Syrah). Provides the highest-confidence pedigree validation tier. Sample metadata needed to map to VIVC names. | 🟠 HIGH | ⬜ TODO
6 | Grapevine Pangenome (Zhou et al. 2024) | Zhou Y. et al. | 2024 | Nature Genetics | 10.1038/s41588-024-01967-5 | Pangenome SNP/SV map 466 accessions 18 phased T2T assemblies | Supplementary Table 1 (466 accession metadata) + Supplementary Data for SNP/kinship matrix From: nature.com/articles/... | 466 accessions with structural variant-aware genotyping. Resolves presence-absence variants invisible to SSR/SNP arrays. Accession metadata table needed to align to VIVC names; kinship data would provide WGS-level parentage validation. | 🟠 HIGH | ⬜ TODO
7 | Myles et al. 2011 — Sample Info Completeness Check | Myles S. et al. | 2011 | PNAS | 10.1073/pnas.1009363108 | SNP genotype metadata [Already have PED/MAP] | Re-download full sample_info.txt from supplementary or original data repository (NCBI BioProject: PRJNA61381) Confirm all 1,817 accessions have variety-name metadata | Validation shows Myles dataset covers only 59 unique child varieties in marker support. Many of the 1,817 accessions may be missing VIVC name alignment. Fetching the complete sample metadata would allow ~10x expansion of the ICS scoring coverage. | 🟠 HIGH | ⬜ TODO
8 | This et al. 2006 — 482 Vitis Accession Diversity | This P. et al. | 2006 | Theor. Appl. Genet. | 10.1007/s00122-006-0340-9 | SSR profiles 482 accessions 20 nSSR loci | Supplementary Table (allele profiles per accession) From: link.springer.com | Covers 482 accessions including many wild and Near Eastern varieties. Provides parentage context for founder varieties at the root of European pedigrees. SSR profiles enable direct cross-source allele matching. | 🟡 MEDIUM | ⬜ TODO
9 | Cipriani et al. 2010 — Northeast Italy SSR | Cipriani G. et al. | 2010 | Theor. Appl. Genet. | 10.1007/s00122-010-1368-y | SSR profiles Northeast Italian varieties 20 nSSR loci | Supplementary Table (allele profiles) From: link.springer.com | Northeast Italian varieties (Veneto, Friuli) are underrepresented in current SSR files. Many VIVC entries for this region have no molecular validation. Expands SSR cross-comparison for this important region. | 🟡 MEDIUM | ⬜ TODO
10 | Ibáñez et al. 2009 — Spanish Varieties SSR | Ibáñez J. et al. | 2009 | Amer. J. Enol. Vitic. | 10.5344/ajev.2009.60.3.306 | SSR profiles Spanish Vitis vinifera OIV 9-locus panel | Supplementary Table (allele profiles) From: ajevonline.org | Spanish varieties (Tempranillo, Garnacha, Albariño lineages) are poorly covered in current SSR files. Oliveira 2020 covers Portugal but Spain needs additional coverage. 854 parent names in the passport have no passport entry — many are Spanish cultivar synonyms. | 🟡 MEDIUM | ⬜ TODO
11 | Vouillamoz & Grando 2006 — Alpine Variety Pedigrees | Vouillamoz J.F. & Grando M.S. | 2006 | Theor. Appl. Genet. | 10.1007/s00122-006-0245-7 | SSR-based parentage assignments Alpine / Central European | Main paper PDF + Supplementary (parentage assignment tables) From: link.springer.com | Resolves parentage for Pinot, Traminer, and Central European founder varieties using the OIV SSR panel. These are high-centrality nodes in the pedigree graph. Several are currently 'undocumented' in the Atlas despite published SSR evidence. | 🟡 MEDIUM | ⬜ TODO
12 | Doligez et al. 2023 — Clone Identification Amplicon | Doligez A. et al. | 2023 | G3: Genes¦Genomes¦ Genetics | 10.1093/g3journal/jkad145 | High-throughput amplicon sequencing clone markers Cab Sauv, Chard, Merlot, Sauv Blanc | Supplementary Table (46 clone-diagnostic markers) From: academic.oup.com/g3journal | Provides clone-level resolution for 4 economically critical cultivars. Useful for disambiguating somatic variants vs. true cultivar-level pedigree relationships. Clone marker table needed to flag potentially misidentified accessions. | 🟡 MEDIUM | ⬜ TODO
13 | Xiao et al. 2025 — Reproductive Systems & Genomics | Xiao H. et al. | 2025 | Nature Communications | 10.1038/s41467-025-56817-7 | Comparative genomics Pinot Noir pedigree panel SFS / IBD data | Supplementary Table (accession list + kinship matrix) + Pinot Noir pedigree metadata From: nature.com/articles/... | Provides IBD coefficients and SFS data for Pinot Noir and related clones. Explains why ICS/ACS scores may deviate from expectation in clonally propagated varieties. Accession metadata needed for VIVC alignment. | 🔵 LOW | ⬜ TODO
14 | Zou et al. 2020 — rhAmpSeq Vitis Core Genome | Zou C. et al. | 2020 | Nature Communications | 10.1038/s41467-019-14280-1 | rhAmpSeq haplotype markers 2,000 loci Multi-species Vitis panel | Contact authors or check NCBI/Dryad for genotype matrix (supplement contained only figures) Email: Cornell Grape Genomics Lab | 2,000 rhAmpSeq haplotype markers with 91.9% transferability across Vitis species. Genotype matrix would enable haplotype-level parentage scoring. Supplement did not include data — may require direct author contact. | 🔵 LOW | ⬜ TODO
15 | European Vitis Database (EVD) eu-vitis.de | JKI / EU consortium | Ongoing | Database | eu-vitis.de | SSR profiles Same OIV 9-locus panel as VIVC ~6,000+ accessions | Request partner/institutional access via eu-vitis.de contact form or through VIVC/JKI contact (SSL cert barrier currently blocks programmatic access) | Would be the most direct cross-validation source for all VIVC SSR parentage calls (identical 9-locus panel). Potentially covers ~6,000+ accessions. Institutional access required — worth a formal request to JKI Siebeldingen. | 🔵 LOW | ⚠️ BLOCKED
16 | Tegopoulos et al. 2025 — Cost-Effective NGS-SNP Panel | Tegopoulos K. et al. | 2025 | Horticulturae (MDPI) | 10.3390/horticulturae11040375 | 14-SNP NGS panel Variety identification | Supplementary Table S1 (14 SNP loci + allele calls per variety tested) From: mdpi.com | 14-SNP panel for variety-level fingerprinting. Useful as a first-pass confirmation layer. Variety list + SNP calls would allow alias resolution for any accession in the panel that is currently unresolved. | 🔵 LOW | ⬜ TODO
17 | VitisGDB Germplasm Accession Table (Wei et al. 2020 — SNP-resolved prime names) | Wei F. et al. | 2020 | Molecular Plant | 10.1016/j.molp.2020.05.010 | Accession metadata table 1,641 entries SNP-resolved VIVC prime names | Download Supplementary Table S1 or accession list from VitisGDB (http://www.vitisdatashare.org or http://vitis.kazusa.or.jp) — 1,641 accessions with prime names validated against VIVC | VitisGDB cross-references all 1,641 accessions to VIVC prime names using SNP data. This table would directly address the ~1,100 unresolved variety name gap in the Atlas alias map. Critical for alias gap resolution at scale. | 🟠 HIGH | ⬜ TODO
18 | PERSEUS Grapevine Pedigree Dataset (Miarnau et al. 2024) | Miarnau X. et al. | 2024 | Bioinformatics | 10.1093/bioinformatics/btae060 | Grapevine pedigree table (literature-curated PO pairs) For cross-validation vs Atlas | Access via PERSEUS web tool: https://bioinformatics.cragenomica.es/perseus — Download grapevine pedigree relationships CSV (built into tool) OR from GitHub: https://github.com/aranzana-lab/PERSEUS | PERSEUS contains literature-curated pedigree relationships for Vitis (and 4 other crops). Comparing PERSEUS grapevine PO pairs against Atlas edges would identify discrepancies requiring manual curation. Provides an independent literature-synthesis validation layer distinct from molecular marker scoring. | 🟡 MEDIUM | ⬜ TODO
19 | Vitis Super-Pangenome 2025 (Canaguier / Nature Genetics) | Canaguier A. et al. | 2025 | Nature Genetics | 10.1038/s41588-025-02111-7 | 72-accession haplotype-resolved genome metadata + kinship matrix (25 wild + 47 cultivated Vitis) | Download Supplementary Table 1 (72 accession metadata) + IBD/kinship matrix if deposited + VCF from NCBI/ENA repository From: nature.com/articles/ s41588-025-02111-7 | Haplotype-aware phylogenomics for 72 Vitis accessions covering global diversity. Disentangles hybridization history invisible to SSR/SNP arrays. Accession metadata + IBD matrix would provide WGS-level parentage ground truth for wild × cultivated hybrid nodes in the Atlas pedigree graph. | 🟡 MEDIUM | ⬜ TODO
20 | Grapevine Pangenome v1.0 Accession Metadata — Zhou et al. 2024 Extension (324 newly sequenced accessions) | Zhou Y. et al. | 2024 | Nature Genetics | 10.1038/s41588-024-01967-5 | Supplementary Table of 466 accession VIVC/prime names + 29-trait phenotypic data | Download Extended Data Table 1 or Supplementary Table 1 (466 accession list with cultivar names and provenance) From: nature.com/articles/ s41588-024-01967-5 | 466 accessions with full SNP/SV map and 29 agronomic trait GWAS. Accession name table is required to align this dataset to the Atlas alias map. Once aligned, kinship coefficients from this resource could provide WGS-level parentage validation for all 466 covered varieties. | 🟡 MEDIUM | ⬜ TODO
21 | Armenian Grape SSR Profiles (OENO One 2022) | Gabrielyan G. et al. | 2022 | OENO One | 10.20870/oeno-one.2022.56.4.4815 | SSR + SNP profiles Armenian cultivars OIV 9-locus panel | Supplementary Table (allele profiles for Armenian cultivars) From: oeno-one.eu/article/view/4815 | Armenia is a primary center of grapevine diversity. Armenian cultivars are poorly represented in current SSR files. SSR profiles using the OIV 9-locus panel would provide direct cross-comparison. Identifies pedigree relationships and synonyms between Armenian and Mediterranean varieties. | 🔵 LOW | ⬜ TODO
22 | Nebbiolo & Barbera Genealogy (Schneider et al. 2020 — Sci. Reports) | Schneider A. et al. | 2020 | Scientific Reports | 10.1038/s41598-020-72799-6 | DNA-based genealogy Nebbiolo, Barbera + related NW Italian cultivars | Main paper PDF + Supplementary Table (pedigree assignments + SSR allele profiles) From: nature.com/articles/ s41598-020-72799-6 | Resolves genealogy of Nebbiolo, Barbera, and ancient Northwestern Italian cultivars using SSR markers. Several Nebbiolo and Barbera parentage nodes are currently 'undocumented' in the Atlas despite clear SSR evidence in this paper. Directly fills pedigree gaps for major wine region varieties. | 🔵 LOW | ⬜ TODO
23 | Crespan et al. 2020 — Glera, Ribolla Gialla & Friuli (Sci. Reports) | Crespan M., Migliaro D., et al. | 2020 | Scientific Reports | 10.1038/s41598-020-64061-w | Vitis18K SNP + cpSSR Friuli Venezia Giulia autochthonous varieties | Main paper PDF + Supplementary Tables (parentage assignments, SSR/SNP allele data) From: nature.com/articles/ s41598-020-64061-w | Resolves parentage of Glera (Prosecco), Ribolla Gialla, and ~30 Friuli autochthonous varieties using the same Vitis18K chip as Lacombe & Emanuelli 2021. Migliaro et al. is a co-author, linking this directly to the Italian fingerprinting panel. Parentage assignments for NE Italian varieties currently listed as 'undocumented' in the Atlas. High integration potential — same chip/loci as an already-integrated source. | 🟡 MEDIUM | ⬜ TODO
24 | De Lorenzis et al. 2019 — Magna Graecia Grapevine Germplasm (BMC Plant Biology) | De Lorenzis G. et al. | 2019 | BMC Plant Biology | 10.1186/s12870-018-1576-y | Vitis18K SNP genotyping ~200 South Italian cultivars Magna Graecia region | Main paper PDF + Supplementary File 1 (accession metadata + parentage assignment table) From: bmcplantbiol.biomedcentral.com/ articles/10.1186/s12870-018-1576-y | SNP-based parentage for ~200 South Italian varieties (Calabria, Sicily, Basilicata) — region with almost no coverage in current Atlas sources. Uses Vitis18K, providing direct compatibility with Lacombe & Emanuelli 2021. Identifies parentage relationships for Gaglioppo, Greco di Tufo, and other Magna Graecia cultivars. Supplementary File 1 likely contains the PO pair table. | 🟡 MEDIUM | ⬜ TODO
25 | Nikoghosyan et al. 2026 — Armenian WGS Population Structure (BMC Plant Biology) | Nikoghosyan M. et al. | 2026 | BMC Plant Biology | 10.1186/s12870-026-08287-2 | Whole-genome sequencing 164 wild + cultivated Armenian Vitis accessions | Main paper PDF + Supplementary Tables (164 accession metadata, kinship/IBD matrix, parentage assignments) From: bmcplantbiol.biomedcentral.com | WGS-level population structure for 164 Armenian wild and cultivated grapevines. Armenia is a primary center of Vitis domestication — wild × cultivated pedigree nodes are poorly represented in all current Atlas sources. WGS IBD matrix provides the highest-confidence parentage tier for Armenian varieties. Accession metadata needed to map to VIVC names. Complements Nikoghosyan & Gabrielyan 2022 SSR panel (row 21) with WGS resolution. | 🟡 MEDIUM | ⬜ TODO

## 02_Already_Integrated
Already Integrated Data Layers
# | Source / Paper | Authors | Year | Journal / DB | DOI | Data File(s) in /data/ | Notes on Current Integration | Status
1 | VIVC Passport Database | Julius Kühn-Institut | 2024 | vivc.de | — | vivc_passport_table.csv vivc_supplementary.csv vivc_doi_scraped.csv | >26,000 varieties. Passport + parent assignments + DOI-scraped bibliography. | ✅ DONE
2 | Myles et al. 2011 (Vitis9KSNP Array) | Myles S. et al. | 2011 | PNAS | 10.1073/pnas.1009363108 | myles_2011_marker_support.csv | 1,817 accessions × 6,114 SNPs. ICS scoring for 59 unique child varieties. NOTE: low coverage — see Sheet 01 row 7 for expansion. | ✅ DONE
3 | Constantini et al. 2026 (Axiom Vitis22K) | Constantini L. et al. | 2026 | Front. Plant Sci. | 10.3389/fpls.2026.1771381 | constantini_2026_marker_support.csv | 145 accessions × 10,484 SNPs. Dosage-based parentage + chloroplast maternal lineage. 96 rows, 57 child varieties. | ✅ DONE
4 | Lacombe et al. 2013 (20-locus SSR) — MOESM2 | Lacombe T. et al. | 2013 | Theor. Appl. Genet. | 10.1007/s00122-012-1988-2 | lacombe_2013_marker_support.csv ssr_lacombe_2013.csv | 828 parentage trios (MOESM2 only). 1,564 marker support rows, 818 child varieties. MOESM7 (SSR profiles) still needed — see Sheet 01 row 2. | ✅ DONE
5 | Oliveira et al. 2020 (SSR — Iberian) | Oliveira H.R. et al. | 2020 | BMC Plant Biology | 10.1186/s12870-020-02585-3 | oliveira_2020_marker_support.csv ssr_oliveira_2020.csv | 88 parentage rows, 34 child varieties. ssr_oliveira_2020.csv fixed Apr 2026: alleles converted from 'A1/A2' combined strings to split numeric columns (ssr_{locus}_a1, ssr_{locus}_a2); '?/?' → NaN. 17 loci × 411 rows now SSR-comparison-ready. | ✅ DONE
6 | GRIN USDA Admixture (DVIT/GVIT, K=5) | USDA-ARS GRIN | 2024 | ars-grin.gov | — | grin_pedigree_support.csv grin_vivc_alignment.csv | 1,257 accessions aligned. 117 trios scored. ACS median 0.923. 19 conflicting, 30 ambiguous alignment entries. | ✅ DONE
7 | Migliaro et al. 2019 (Italian SSR) | Migliaro D. et al. | 2019 | Published dataset | — | migliaro_vivc_match.csv ssr_migliaro_2019.csv | 230 Italian varieties × 16 SSR loci (VVS2, VVMD5-7, 25, 27, 28, VrZAG62, VrZAG79). Clean — 0 format errors. | ✅ DONE
8 | Curated SSR literature (hand-curated pairs) | Various | Various | Multiple journals | Various | marker_support.csv | 59 rows, 37 child varieties. Highest confidence tier: 47 confirmed, 11 probable, 1 disputed. Manually curated. | ✅ DONE
9 | VIVC Confirmed Marker Support (parsed from passport text) | VIVC | 2024 | vivc.de | — | vivc_confirmed_marker_support.csv | 3,391 rows, 1,695 child varieties — all 'confirmed'. 304 child names not resolving to passport (alias expansion needed). | ✅ DONE
10 | Lacombe & Emanuelli 2020 (Italian Parentage Atlas, Vitis18K SNP) | Lacombe T., Emanuelli F. et al. | 2020/2021 | Front. Plant Sci. | 10.3389/fpls.2020.605934 | lacombe_emanuelli_2020_marker_support.csv | INTEGRATED Apr 2026. SupplementaryFile5 (829 PO duos) + SupplementaryFile7 (189 trios). 1,716 rows total, 775 unique child varieties. Confirmed: 34, probable: 1,676, disputed: 6. Sections: A=new this study (206), C=confirming prior (27), D=previously published (1,477), B=invalidating (6). | ✅ DONE
11 | Laucou et al. 2018 (10K Genome-wide SNPs, PLOS ONE) | Laucou V. et al. | 2018 | PLOS ONE | 10.1371/journal.pone.0192540 | laucou_2018_marker_support.csv | INTEGRATED Apr 2026. S2 table (118 trios) + S4 table (490 PO pairs). 1,196 rows total, 460 unique child varieties. Confirmed: 216 (trios with prior publication), probable: 980 (PO pairs + new trios). FAMOZ + KING dual validation for all pairs. confirmed_year set to 2018. | ✅ DONE
12 | Constantini et al. 2026 (Axiom Vitis22K SNP, Frontiers) | Constantini L. et al. | 2026 | Front. Plant Sci. | 10.3389/fpls.2026.1771381 | constantini_2026_marker_support.csv | 96 rows, 57 child varieties — all 'confirmed'. Includes Cabernet Sauvignon, Pinot Noir, Vermentino lineages. 18 rows use Vitis9KSNP (10,484 SNPs); 78 rows use Axiom Vitis22K (22,000 SNPs). n_markers fixed Apr 2026 (was NaN for 78 rows). | ✅ DONE
13 | Liang et al. 2019 (472 Vitis WGS — Nat. Commun.) | Liang Z. et al. | 2019 | Nature Communications | 10.1038/s41467-019-09135-8 | liang_2019_marker_support.csv | INTEGRATED Apr 2026 from MOESM4 (cultivated V. vinifera section). 208 rows, 108 unique child varieties, 79 net-new (not in any other source). Passport-reported parentage from VIVC/GRIN accession records. All rows: probable confidence, passport evidence_type. Expands East Asian (Japanese/Chinese) and American table grape coverage substantially. | ✅ DONE

## 03_Data_Quality_Fixes
Internal Data Quality Fixes (No Download Required)
# | File / Layer | Issue Type | Count | Description & Fix | Action Required | Priority | Status
1 | marker_name_aliases.csv + All marker support files | Alias Gap | ~1,100+ names | Child and parent variety names in marker support files that do not resolve to any passport entry after alias lookup. Majority are likely synonyms, regional names, or accession-code variants of VIVC-registered varieties. | Semi-automated curation: run fuzzy matching (difflib/rapidfuzz) against passport prime_names. Flag top-50 candidates per unresolved name for manual accept/reject. Add confirmed matches to marker_name_aliases.csv. | 🔴 CRITICAL | ⬜ TODO
2 | ssr_oliveira_2020.csv | Non-numeric Alleles → FIXED | 156 cells | FIXED Apr 2026: All 411 rows × 17 loci reformatted from combined 'A1/A2' strings (e.g. '189/193') into split numeric columns (ssr_{locus}_a1, ssr_{locus}_a2). '?/?' entries converted to NaN. NaN rate 6.8% (appropriate for Oliveira panel which uses 17 loci vs. the standard 9, with gaps in Portuguese-specific loci). File now has 37 columns (variety_name, vivc_match, source, 17×2 allele cols). | RESOLVED: Re-parsed Oliveira 2020 allele table by splitting on '/' separator. Residual '/' chars in allele columns = 0 after fix. | 🟠 HIGH | ✅ DONE
3 | vivc_confirmed_marker_support.csv | Unresolved Child Names | 304 entries | 304 child variety entries in vivc_confirmed_marker_support.csv do not match any passport prime_name after alias resolution. These likely represent alternate capitalizations, accession codes in parentheses, or varieties whose VIVC name changed since the record was created. | Extract the 304 names (see Sheet 08_Orphan_Varieties in validation report). Run fuzzy match against passport. Add confirmed aliases to marker_name_aliases.csv. For true mismatches, flag for manual review. | 🟠 HIGH | ⬜ TODO
4 | lacombe_2013_marker_support.csv | Unresolved Child Names | 734 entries | 734 child variety names from Lacombe 2013 parentage table do not resolve to passport entries. Lacombe 2013 used slightly different variety naming conventions (e.g. accented characters, Provençal spellings) that diverge from VIVC canonical names. | Cross-reference Lacombe 2013 MOESM1 (passport with VIVC numbers) against current passport. Build name-to-VIVC-number mapping, then add all resolved aliases to marker_name_aliases.csv. | 🟠 HIGH | ⬜ TODO
5 | vivc_passport_table.csv | Self-Parent Entries | 259 (P1) + 260 (P2) = 519 | 519 rows where parent name equals child name — data entry errors in the VIVC source data. The app filters these at runtime but they create noise in validation and could corrupt graph traversal if the filter is ever bypassed. | These originate in the VIVC scrape. The scraping artefact (row 0 = header, row 1 = valid values, rows 2+ = data) causes the berry color / utilization valid-values row to be misread as parent names for the first entries. Confirm source and fix in the passport loading function. | 🟡 MEDIUM | ⬜ TODO
6 | vivc_passport_table.csv | Duplicate Prime Names | 215 names (710 rows) | 215 prime names appear in more than one row. These are likely varieties registered under the same name in multiple VIVC scrape pages, or genuine synonyms with identical canonical names assigned to distinct accessions. | Deduplicate by VIVC number (keep lowest), then by prime name. Already handled at runtime in app.py — but should be resolved in the raw file to avoid confusion during offline analysis. | 🟡 MEDIUM | ⬜ TODO
7 | node_molecular_profile.csv | Missing VrZAG62 / VrZAG79 SSR Loci | 48 / 1,841 nodes have these loci | Two of the 9 OIV standard loci (VrZAG62, VrZAG79) are present in only 48 of 1,841 node profiles. These loci are present in Migliaro 2019 SSR data but not in Lacombe 2013 (which only covers 7 of 9 loci). The absence reduces genotype comparison power for the majority of the panel. | NOTE Apr 2026: Laucou 2011 DOI confirmed invalid — that paper does not exist (see Sheet 01 row 4). For VrZAG62/VrZAG79, use Migliaro 2019 (already integrated) and Lacombe 2013 MOESM3-6 supplementary if obtainable. When Lacombe 2013 MOESM7 allele profiles are secured (Sheet 01, row 2), re-run build_node_molecular_profile.py to fill these two loci. | 🟡 MEDIUM | ⬜ TODO
8 | grin_pedigree_support.csv | Ambiguous GRIN Alignment | 11 child + 6 P1 + 13 P2 = 30 trios | 30 trio members have ambiguous GRIN alignment — i.e. more than one GRIN accession matches the VIVC name. The current pipeline uses the first match. For these 30 cases, the ACS score may reflect the wrong accession's admixture profile. | For each ambiguous case, compare admixture profiles of all candidate accessions and select the one with passQC=True. If multiple passQC accessions exist, average their profiles or flag the trio as 'ambiguous' in the confidence field rather than assigning a definitive ACS. | 🟡 MEDIUM | ⬜ TODO
9 | constantini_2026_marker_support.csv | Unresolved Child Names | 59 entries | 59 of 96 Constantini 2026 child variety entries do not resolve to passport. These are likely accession labels used in the Axiom array rather than VIVC prime names. | Cross-reference Constantini et al. 2026 Supplementary Table 6 (which lists the 145 samples with full metadata) to extract VIVC numbers or prime names for all 145 accessions. Add to alias map. | 🔵 LOW | ⬜ TODO

## 04_Supplementary_File_Guide
Exact Supplementary Files to Download — Per Paper
# | Paper | DOI | Exact File(s) to Download | Where to Find Them | Columns / Format Expected | Priority
1 | Lacombe & Emanuelli et al. 2020/2021 | 10.3389/fpls.2020.605934 | Supplementary Table 2 (parent-offspring pairs) + Supplementary Table 3 (parent-parent-offspring trios) | frontiersin.org → article page → Supplementary Material (look for .xlsx or .csv links below abstract) | Expected columns: child_name ¦ parent1_name ¦ parent2_name ¦ vivc_no ¦ confidence ¦ n_loci May also include SNP-based LOD scores | 🔴 CRITICAL
2 | Lacombe et al. 2013 (MOESM7 only) | 10.1007/s00122-012-1988-2 | MOESM7_ESM — the '276 unrelated reference varieties' SSR allele profile table | link.springer.com → article → Supplementary Information → download MOESM7_ESM (distinct from MOESM2 already in hand) | Expected columns: variety_name ¦ vivc_no ¦ VVS2_a1 ¦ VVS2_a2 ¦ VVMD5_a1 ¦ VVMD5_a2 ... (20 loci × 2 alleles = 40 allele columns) | 🔴 CRITICAL
3 | Sefc et al. 2000 | 10.1023/A:1018609920920 | Main paper PDF only (Tables 2–3 — allele frequency tables for 9 OIV loci) | link.springer.com → TAG Vol 100 Or via institutional access No separate supplement — extract from PDF Table 2 (frequencies) and Table 3 (diversity stats) | Manual extraction → CSV: locus ¦ allele ¦ frequency (9 loci × all alleles) Needed for LOD score computation | 🔴 CRITICAL
4 | Laucou et al. 2011 [⚠️ DOI INVALID — SKIP] | 10.1371/journal.pone.0021265 | — INVALID ENTRY — This paper does not exist. See Sheet 01 row 4 for details. | DO NOT PURSUE — cataloguing error. DOI resolves to a marine LiDAR paper. Equivalent data is in Lacombe 2013 (integrated) and Laucou 2018 (integrated). | N/A — replaced by Lacombe 2013 and Laucou 2018 (both integrated) | ⚠️ INVALID
5 | Magris et al. 2021 | 10.1038/s41467-021-27487-y | Supplementary Data 1 (sample metadata — 204 accessions) + Supplementary Data 3 or 4 (kinship / relatedness matrix if provided) | nature.com/articles/s41467-021-27487-y → Supplementary Information (look for Excel or CSV links near 'Source Data' section) Also: ENA / NCBI linked accessions | Metadata: accession_id ¦ cultivar_name ¦ subspecies ¦ origin ¦ VIVC_name Kinship: n×n matrix or pairwise IBD table with accession IDs | 🟠 HIGH
6 | Myles et al. 2011 (sample_info check) | 10.1073/pnas.1009363108 | Re-download complete sample_info.txt from NCBI BioProject PRJNA61381 (SRA study SRP002760) | ncbi.nlm.nih.gov/bioproject/ PRJNA61381 → SRA Experiments → sample attributes OR via SRA Run Selector | Columns: local_id ¦ cultivar_name ¦ origin ¦ ploidy ¦ GRIN_PI_number (confirm all 1,817 samples have cultivat-name metadata) | 🟠 HIGH
7 | Zhou et al. 2024 (Pangenome) | 10.1038/s41588-024-01967-5 | Supplementary Table 1 (466 accession metadata) + any pairwise kinship or variant matrix if provided | nature.com/articles/s41588-024-01967-5 → Supplementary Information Also check Figshare / Zenodo DOI listed in Data Availability section | Metadata: accession_id ¦ cultivar_name ¦ origin ¦ ploidy ¦ VIVC_no Variant data: VCF or allele matrix | 🟠 HIGH
8 | Vouillamoz & Grando 2006 | 10.1007/s00122-006-0245-7 | Main paper PDF + Supplementary Table (parentage assignments + SSR allele profiles) | link.springer.com → TAG → Electronic Supplementary Material | variety_name ¦ parent1 ¦ parent2 ¦ n_loci ¦ LOD_score + allele profiles for OIV loci | 🟡 MEDIUM
9 | Doligez et al. 2023 | 10.1093/g3journal/jkad145 | Supplementary Table (46 validated clone markers: SNV/InDel positions + alleles per clone for 4 cultivars) | academic.oup.com/g3journal → article → Supplementary data (look for .xlsx attached to article) | cultivar ¦ clone_id ¦ marker_id ¦ chromosome ¦ position ¦ ref_allele ¦ alt_allele ¦ clone_assignment | 🟡 MEDIUM
10 | Cipriani et al. 2010 | 10.1007/s00122-010-1368-y | Supplementary Table (SSR allele profiles for NE Italian varieties) | link.springer.com → TAG → Electronic Supplementary Material | variety_name ¦ origin ¦ VVS2_a1 ¦ VVS2_a2 ... (OIV 9-locus or 20-locus panel) | 🟡 MEDIUM
11 | Ibáñez et al. 2009 | 10.5344/ajev.2009.60.3.306 | Main paper PDF + Supplementary Table (Spanish variety SSR profiles) | ajevonline.org → Vol 60 Issue 3 OR request from corresponding author (CSIC Zaragoza) | variety_name ¦ origin ¦ region ¦ OIV_locus_profiles | 🟡 MEDIUM
12 | VitisGDB (Wei et al. 2020) — Accession Table | 10.1016/j.molp.2020.05.010 | Supplementary Table S1 (1,641 accession list with SNP-verified prime names) OR export from VitisGDB portal | http://www.vitisdatashare.org OR http://vitis.kazusa.or.jp → Germplasm module → Export (look for 'Download all' option) | prime_name ¦ vivc_no ¦ subspecies ¦ origin ¦ genome_accession ¦ WGS_coverage | 🟠 HIGH
13 | PERSEUS Grapevine Pedigree (Miarnau et al. 2024) | 10.1093/bioinformatics/btae060 | Grapevine pedigree relationship CSV (download from PERSEUS tool or GitHub repository) | https://bioinformatics.cragenomica.es/perseus → select Vitis → Export CSV OR GitHub: https://github.com/aranzana-lab/PERSEUS → data/ folder → vitis_pedigree.csv (or similar) | child_name ¦ parent1_name ¦ parent2_name ¦ year ¦ source_DOI (literature-curated, no confidence scores) | 🟡 MEDIUM
14 | Vitis Super-Pangenome 2025 (Canaguier / Nature Genetics) | 10.1038/s41588-025-02111-7 | Supplementary Table 1 (72 accession metadata) + IBD/kinship coefficients if deposited separately | nature.com/articles/ s41588-025-02111-7 → Supplementary Information + Data Availability section (check Zenodo/Figshare DOI) | accession_id ¦ cultivar_name ¦ subspecies ¦ origin ¦ wild/cult ¦ genome_accession ¦ haplotype | 🟡 MEDIUM
15 | Schneider et al. 2020 — Nebbiolo Genealogy (Sci. Reports) | 10.1038/s41598-020-72799-6 | Main paper PDF + Supplementary Table (SSR profiles + parentage assignments for NW Italian varieties) | nature.com/articles/ s41598-020-72799-6 → Supplementary Information → download supplementary tables | variety_name ¦ parent1 ¦ parent2 ¦ n_SSR_loci ¦ LOD_score ¦ allele_profiles (OIV 9-locus) | 🔵 LOW

## 05_Integration_Roadmap
Integration Roadmap — Ordered Workflow After Downloads
Step | After Obtaining | Script to Write / Modify | Input File(s) | Output File(s) | Depends On | Status
1 | Lacombe & Emanuelli 2020 (Supp Files 5 & 7) + Laucou 2018 (S2 & S4) | build_lacombe_emanuelli_2020 _support.py ✅ build_laucou_2018_support.py ✅ (both completed Apr 2026) | SupplementaryFile5.xlsx SupplementaryFile7.xlsx pone.0192540.s002.xlsx pone.0192540.s004.xlsx | lacombe_emanuelli_2020 _marker_support.csv ✅ laucou_2018_marker_support .csv ✅ | None | ✅ DONE
2 | Lacombe 2013 MOESM7 (276 reference SSR profiles) | Extend build_lacombe_ssr _profiles.py to parse MOESM7 (new section in existing script) | 122_2012_1988_MOESM7_ESM.xlsx (or .pdf) | ssr_lacombe_2013_reference276.csv | Step 1 | ⬜ TODO
3 | Sefc et al. 2000 (allele frequency tables from PDF) | Manual extraction → sefc_2000_allele_freqs.csv then: build_lod_score_module.py (new utility) | sefc_2000_table2.csv (manual extraction from PDF) | sefc_2000_allele_freqs.csv lod_score_utils.py | None | ⬜ TODO
4 | Laucou 2011 INVALID — use Laucou 2018 (~783 SSR profiles, already integrated) | — No script needed — Laucou 2018 already integrated (laucou_2018_marker_support.csv) | — already done — | laucou_2018_marker_support.csv (1,196 rows; 460 child varieties) | ✅ Complete (superseded by Laucou 2018) | ✅ DONE
5 | Steps 2–3 complete | Extend build_node_molecular _profile.py to pull VrZAG62 + VrZAG79 from Migliaro 2019 and Lacombe 2013 MOESM3-6 | ssr_migliaro_2019.csv ssr_lacombe_2013_reference276.csv | node_molecular_profile.csv (updated — all 9 OIV loci filled) | Steps 2, 3 | ⬜ TODO
6 | Alias gap curation (fuzzy match output reviewed) | Run fuzzy_alias_expander.py (new script using rapidfuzz) → user reviews candidates → accepted pairs added to marker_name_aliases.csv | marker_name_aliases.csv (all marker support CSVs as input) | marker_name_aliases.csv (updated — ~1,100+ new entries) | None (parallel with Steps 1–4) | ⬜ TODO
7 | Oliveira SSR re-check (non-numeric allele fix) | Update build_oliveira_ssr _support.py: handle '0/0' and text-format allele pairs | Oliveira 2020 Supp (original) ssr_oliveira_2020.csv | ssr_oliveira_2020.csv (updated — 156 cells fixed) | None (parallel) | ⬜ TODO
8 | Magris et al. 2021 (204 WGS sample metadata) | build_magris_wgs_pedigree _support.py (IBD-based parentage scoring) | magris_2021_supp_data1.xlsx (+ kinship matrix if available) | magris_2021_pedigree_support.csv | Step 6 (alias map expanded) | ⬜ TODO
9 | All Steps 1–8 complete | Re-run app.py load_marker _support() — verify combined table row counts + re-run validation script | All updated CSVs | Grapevine_Pedigree_Atlas _Validation_{date}.xlsx (updated report) | Steps 1–8 | ⬜ TODO
10 | Step 9 validated | Update manuscript Sections 3 & 9 + Table 2 with new source coverage statistics | Validation report | Grapevine_Pedigree_Atlas _Manuscript_{date}.docx (updated) | Step 9 | ⬜ TODO
11 | VitisGDB accession table + PERSEUS pedigree CSV (Queue rows 17, 18) | run_comparable_tools _crosscheck.py (new script) → compare Atlas edges vs PERSEUS → alias match VitisGDB names | vitisGDB_accessions.csv perseus_vitis_pedigree.csv marker_name_aliases.csv | comparable_tools_discrepancies.csv marker_name_aliases.csv (updated with VitisGDB names) | Step 6 (alias map) | ⬜ TODO
12 | Super-Pangenome 2025 + Zhou 2024 accession tables (Queue rows 19, 20) | build_pangenome_wgs _pedigree_support.py (new script) → IBD-based validation for 72 + 466 accessions | super_pangenome_2025 _supp_table1.csv zhou_2024_accessions.csv | pangenome_pedigree_support.csv | Step 6 (alias map), Step 8 | ⬜ TODO